## Project Overview
|  |  | May | [30 empty] | June
|  | Week (#) | 1 | [5 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9
|  | Day(#) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sprint | Activity | Progress
1 - SERVER | Home Page
| Welcome Page | 100%
| Database System | 100%
| Download Page | 100%
| Parsing System | 100%
2 - CLIENT | Section Start
| GUI | 100%
| Map | 100%
| Sound Test System | 100%
Section Login
| GUI | 100%
| OAUTH | 100%
| Integration | 100%
Section Offline Main
| GUI | 100%
| Settings System | 100%
| Recognition Type | 100%
| Integration | 100%
Section Online Main
| Information System | 100%
| Map visualization | 100%
| Allert System | 100%
| Localization Operations | 100%
| Disconnection System | 100%
| Cucumber | 100%
| Integration | 100%
Legend
Completed
In Progress
Planned

## Daily Planning
Task Estimation |  | Daily Planning
| Estimates (hours) |  | Daily Work |  | Total Balance
Task | # | Day | Planned | Actual | Planned | Actual | Notes
Set homepage routes on Ruby | 1 | 2018-09-05 | 0 | 0 | 35 | 35
Make homapage html | 1 | 2018-05-10 | 3 | 2 | 32 | 33
Make quake-report route | 2 | 2018-05-11 | 8 | 7 | 24 | 26
Make parsing Operations | 2 | 2018-05-12 | 10 | 8 | 14 | 18
Database Operations | 3 | 2018-05-15 | 4 | 3 | 10 | 15
Set Json Object style | 1 | 2018-05-16 | 2 | 2 | 8 | 13
Make principal GUI | 1 | 2018-05-17 | 3 | 2 | 5 | 11
Set map on GUI | 3 | 2018-05-20 | 2 | 2 | 3 | 8
Make login panel | 1 | 2018-05-22 | 8 | 8 | 0 | 0 | Finish!
Make the buttons listener | 1
Login Main functios | 1
Make Outh function | 3
Make application principals fuctions | 3
Create loop function | 1
Make place operations | 2
Set place on map | 2
Create get info function | 1
Set resoults on GUI | 1
Cucumber | 3
Make settings panel | 2
TOT: 19 Task | 35 Hours